## Legend
Points | Bug Severity | Description
1 | Low (Non-Critical) | Unimportant. Typo error or small user interface alignment issues. | Points < 10 | Use the planned debugging time in the iteration.
5 | Medium | Bugs that affect the less important functionalities (i.e. wrong output), however the application still can run and will not crash. | Points >= 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
10 | Critical | Major bug that will cause the application to crash and severely hinder the progress of the schedule. Iteration must be stopped immediately and bug must be resolved before proceeding

## Graph Information
Iteration | Total Number of bugs | Total bug score | Severity
|  |  | Medium | Low | Critical
1 | 10 | 30 | 5 | 5 | 0
2 | 11 | 28 | 2 | 8 | 1
3 | 10 | 34 | 6 | 4 | 0
4 | 15 | 51 | 6 | 9 | 0
5 | 10 | 26 | 6 | 7 | 0

## Bug Metrics - Iteration 1
S/N | Bug Description | Bug Severity | Function Affected | Mitigation Plan | Status
1 | User is able to access application pages via direct URL even after logging out. | Medium | Application Login | To be fixed during debugging (14th Sept) | Resolved
2 | Faulty Admin Page Validation where Admin does not have to validate password before entering the panel | Medium | Access to Admin Panel for Bootstrap / Upload | To be fixed during debugging (14th Sept) | Resolved
3 | Faulty Admin Panel session management whereby admin booted out of admin panel upon uploading/bootstrapping | Medium | Access to Admin Panel for Bootstrap / Upload | To be fixed during debugging (15-16th Sept) | Resolved
4 | Application does not reject duplicated mac_addresses when uploaded from demographics.csv | Medium | Bootstrap Data validation | To be fixed during debugging (15-16th Sept) | Resolved
5 | Application does not currently detect or correct duplicate rows in the location.csv entries | Medium | Bootstrap Data validation | To be fixed during debugging (15-16th Sept) | Resolved
6 | Output displays error on multiple rows for a specific line validated instead of all on the same line | Low | Bootstrap Result Display | To be fixed during debugging (15-16th Sept) | Resolved
7 | Output displays the error headers even though there are no errors | Low | Bootstrap Result Display | To be fixed on Iteration 2 | Resolved
8 | Pressing of Bootstrap/Upload Button Without Choosing File | Low | Bootstrap Data validation | To be fixed on Iteration 2 | Resolved
9 | Adding "wilhelm.kong.2012@hotmail.com" to an email entry doesn't return an "invalid domain" error | Low | Bootstrap Result Display | To be fixed on Iteration 2 | Resolved
10 | Add an invalid school name to an email entry e.g. wilma.lam.2010@soc sci.smu.edu.sg doesn't return a an "invalid email" error | Low | Bootstrap Data validation | To be fixed on Iteration 2 | Resolved
Initial Total Number of Bugs = 5 Medium and 5 Low Initial Total Score = 30 Number of Bugs Resolved = 5 Medium and 2 Low Total Score Resolved = 27

## Bug Metrics - Iteration 2
S/N | Bug Description | Bug Severity | Function Affected | Mitigation Plan | Status
1 | Breakdown Functionality crashes when selecting any input | Critical | Basic Location Report Breakdown | To be fixed immediately (To be fixed immediately) | Resolved
2 | Output displays maximum count of 1 despite there being multiple counts of users within a timeframe (Test Case 1). | Medium | Top-K Next Places Result Validation | To be fixed during debugging (7th Oct) | Resolved
3 | No validation of empty fields and invalid email and date and time | Medium | Top-K Companions Result Validation | To be fixed during debugging (7th Oct) | Resolved
4 | Pressing of Bootstrap/Upload Button Without Choosing File | Low | Bootstrap Data validation | To be fixed on Iteration 2 | Resolved
5 | Adding "wilhelm.kong.2012@hotmail.com" to an email entry doesn't return an "invalid domain" error | Low | Bootstrap Result Display | To be fixed on Iteration 2 | Resolved
6 | Add an invalid school name to an email entry e.g. wilma.lam.2010@soc sci.smu.edu.sg doesn't return a an "invalid email" error | Low | Bootstrap Data validation | To be fixed on Iteration 2 | Resolved
7 | Ranking display is incorrect. K-value of 3 must be specified to attain 3 results of Rank 1 instead of obtaining all 3 with K-value 1 (Test Case 1). | Low | Top-K Next Places Result Display | To be fixed during debugging (7th Oct) | Resolved
8 | Display of users found and users that visited another place constantly shows 0 (Test Case 1). | Low | Top-K Next Places Result Display | To be fixed during debugging (7th Oct) | Resolved
9 | Unable to display all places belonging of the same rank with the number of people in that location for query date and time. | Low | Top-K Popular Places Result Validation | To be fixed during debugging (7th Oct) | Resolved
10 | Unable to display all companions belonging of the same rank. | Low | Top-K Companions Result Validation | To be fixed during debugging (7th Oct) | Resolved
11 | Display Exception report after inputting wrong format of date and time | Low | Top-K Next Places Result Display | To be fixed during debugging (7th Oct) | Resolved
Initial Total Number of Bugs (Excluding 3 Low Bugs from Iteraton 1) = 1 Critical, 2 Medium and 5 Low Initial Total Score = 25 Number of Bugs Resolved (Including Bugs from Iteration 1) = 1 Critical, 2 Medium and 8 Low Total Score Resolved = 28

## Bug Metrics - Iteration 3
S/N | Bug Description | Bug Severity | Function Affected | Mitigation Plan | Status
1 | Basic Breakdown functionality returns null with invalid token | Medium | JSON for Breakdown by year, gender and school | To be fixed during debugging | Resolved
2 | No validation of origin / semantic place | Medium | JSON for Top-K Next Places | To be fixed during debugging | Resolved
3 | Able to get pass invalid origin e.g. SMUSISB/SMUSISL | Medium | JSON for Top-K Next Places | To be fixed during debugging | Resolved
4 | 5 min time interval in breakdown report should be 300000 milliseconds instead of 30000 seconds | Medium | JSON for Breakdown by year, gender and school | To be fixed during debugging | Resolved
5 | Duplicated sub-groups are displayed | Medium | Automatic Group Detection | To be fixed during debugging | Resolved
6 | Incorrect time spent displayed | Medium | Automatic Group Detection | To be fixed during debugging | Resolved
7 | Logged in users still able to assess index.jsp | Low | Authentication | To be fixed during debugging | Resolved
8 | Login as a invalid non-admin user and it displays wrong error message. It should display "invalid username/password" but it displays "Invalid invalid password". | Low | Authentication | To be fixed during debugging | Resolved
9 | Admin is able to access more functions that what is supposed to. E.g. admin can access heatmap, Basic location report e.t.c. | Low | Authentication | To be fixed during debugging | Resolved
10 | ErrorUtility BLANK_ORIGIN attribute stores the value "blank date" instead of "blank origin" | Low | JSON for Top-K Next Places | To be fixed during debugging | Resolved
Initial Total Number of Bugs = 6 Medium and 4 Low Initial Total Score = 34 Number of Bugs Resolved = 6 Medium and 4 Low Total Score Resolved = 34

## Bug Metrics - Iteration 4
S/N | Bug Description | Bug Severity | Function Affected | Mitigation Plan | Status | Fixed By | SVN Rev No.
1 | JSON authenticate does not display any output when valid parameters used | Medium | JSON Authenticate | To be fixed during debugging | Resolved | Ranon & Shaun | 268
2 | Invalid email such as @sis.sis.smu.edu.sg did not display error | Medium | Bootstrap/Upload | To be fixed during debugging | Resolved | Ranon & Shaun | 265
3 | Duplicated row is correctly displayed as an error, but the row inserted into the database corresponds to the errornous row | Medium | Bootstrap/Upload | To be fixed during debugging | Resolved | Ranon & Shaun | 265
4 | SMUSISL0 is accepted as a valid floor and semantic location | Medium | Bootstrap/Upload | To be fixed during debugging | Resolved | Ranon & Shaun | 265
4 | Token is not validated for JSON Bootstrap | Medium | JSON Bootstrap | To be fixed during debugging | Resolved | Ranon & Shaun | 265
5 | AGD results sometimes incorrect because a specific pair is not considered (check pair with mac-add starting with a203, timestamp 2014-03-24 13:17:00, dataset HE v1) | Medium | Automatic Group Detection | To be fixed during debugging | Resolved | Ai Xin and Yiyi | 258
6 | AGD results sometimes incorrect, when dealing with pairs that each have update at the same location but non-overlapping timestamps between each pair | Medium | Automatic Group Detection | To be fixed during debugging | Resolved | Ai Xin and Yiyi | 259
7 | Basic Next places results doesn't display queried semantic place where applicable | Medium | Basic Next Places | To be fixed during debugging | Resolved | Ranon & Shaun | 264
8 | Incorrect error "invalid row records" is displayed instead of "blank <field>" when bootstrapping | Medium | Bootstrap/Upload | To be fixed during debugging | Resolved | Ranon & Shaun | 265
9 | URL for main admin page should end with "/admin" | Low | Bootstrap/Upload | To be fixed during debugging | Resolved | Ranon & Shaun | 263
10 | Error display is inconsistent with Wiki requirements for Bootstrap/Upload | Low | Bootstrap/Upload | To be fixed during debugging | Resolved | Ranon & Shaun | 265
11 | Field for group count is erroneously called "count", inconsistent with wiki requirements | Low | JSON Group Aware Next Places | To be fixed during debugging | Resolved | Ranon & Shaun | 253
12 | Group Aware Popular Places does not display any message, ie. "No member records found, etc" when no results are found | Low | Group Aware Popular Places | To be fixed during debugging | Resolved | Ai Xin and Yiyi | 262
13 | Group Aware Popular Places results do not display in lexicographical order of semantic places when ranks are tied | Low | Group Aware Popular Places | To be fixed during debugging | Resolved | Ai Xin and Yiyi | 258
14 | Heatmap result display incorrect count for population | Low | Heatmap | To be fixed during debugging | Resolved | Ai Xin and Yiyi | 261
Initial Total Number of Bugs = 9 Medium and 6 Low Initial Total Score = 51 Number of Bugs Resolved = 9 Medium and 6 Low Total Score Resolved = 51

## Bug Metrics - Iteration 5
S/N | Bug Description | Bug Severity | Function Affected | Mitigation Plan | Status | Fixed By | SVN Rev No.
1 | UAT checker does not obtain the secretToken stored in the session | Medium | All JSON Web Services | To be fixed during debugging | Resolved | Aixin & Benjamin | 309
2 | Top-K Next Places displays incorrect result (UAT Test Case 15) | Medium | Top-K Next Places | To be fixed during debugging | Resolved | Ranon & Yiyi | 314
3 | Results of Top-K Popular Places is wrong. (UAT Test Case 12) | Medium | Top-K Popular Places | To be fixed during debugging | Resolved | Aixin & Benjamin | 310
4 | UAT Autochecker displays invalid Bootstrap result (extra invalid semantic-place) (Test Case 23) | Medium | Bootstrap/Upload | To be fixed during debugging integrated functionalities | Resolved | Ranon & Yiyi | 326
5 | Upload functionality does not display number of rows loaded and errors despite entries being logged into the database | Medium | Bootstrap/Upload | To be fixed during debugging integrated functionalities | Resolved | Ranon & Yiyi | 334
6 | Heatmap for B1 still shows traces without a map attached | Medium | Heatmap | To be fixed during debugging integrated functionalities | Resolved | Ranon & Yiyi | 319
7 | Number of records loaded is displayed as a String, not a number | Low | Bootstrap/Upload | To be fixed during debugging | Resolved | Aixin & Benjamin | 309
8 | Year is displayed as a String, not a number | Low | Basic Location Report Breakdown by Year, Gender, School | To be fixed during debugging | Resolved | Aixin & Benjamin | 309
9 | Result is not sorted lexicographically | Low | Top-K Popular Places | To be fixed during debugging | Resolved | Aixin & Benjamin | 310
10 | Result does not retain capital letter for email when inserted into Database (UAT Test Case 13,14) | Low | Top-K Companion | To be fixed during debugging | Resolved | Aixin & Benjamin | 309
11 | AGD for JSON is incorrect display of "total groups" instead of "total group" | Low | Automatic Group Detection | To be fixed during debugging | Resolved | Ranon & Yiyi | 306
12 | No percentage valued displayed for Basic and Group Next Places Report | Low | Bootstrap/Upload | To be fixed during debugging | Resolved | Ranon & Yiyi | 342
13 | Graphical UI for heatmap level 2 shows density when there are no traces found | Low | Heatmap | To be fixed during debugging | Resolved | Ranon & Yiyi | 341
14 | Letter "s" found at Top-k Companions jsp page | Low | Top-K Popular Places | To be fixed during debugging | Resolved | Ranon & Yiyi | 339
15 | UI for Bootstrap does not display tabular format for sucesses / overall results | Low | Bootstrap/Upload | To be fixed during debugging integrated functionalities | Resolved | Ranon & Yiyi | 321
Initial Total Number of Bugs = 6 Medium and 9 Low Initial Total Score = 39 Number of Bugs Resolved = 6 Medium and 7 Low Total Score Resolved =