## Rubrics
Score(%) | Action
PPM < 50 | 1.Re-estimate the tasks in the coming iteration(s) and update the schedule document.
2.Review possible pairing & estimation issues.
50 < PPM <= 150 | No action required.
150 < PPM | 1.Re-estimate the tasks in the coming iteration(s) and update the schedule document.
2.Review possible pairing & estimation issues.

## PPlog
Iteration 1 - Breakdown According to Specific Coding (PPLOG) Task
Iteration | Task Description | Planned Duration (min) | Actual Duration (min) | Value/Score | Overrun/Underrun | Minutes Overrun/Underrun | Coders
1 | Login module - Full functionality | 45 | 34 | 1.32 | Okay | -11 | Benjamin + Yiyi
| Set up database schema, tables and JDBC connection | 120 | 105 | 1.14 | Okay | -15 | Benjamin + Yiyi
| Login module - Full functionality | 75 | 49 | 1.53 | Underrun | -26 | Benjamin + Yiyi
| Bootstrap Module (Individual Uploads, Admin Panel, Validation Servlet) | 120 | 123 | 0.98 | Okay | 3 | Aixin + Shaun
| Bootstrap Module (Individual Uploads, Admin Panel, Validation Servlet) | 180 | 181 | 0.99 | Okay | 1 | Aixin + Shaun
| UI Framework (Login, Main page, Admin Panel, other links) using Twitter Bootstrap | 300 | 296 | 1.01 | Okay | -4 | Benjamin + Yiyi
| Bootstrap Module (Zip uploads) | 120 | 121 | 0.99 | Okay | 1 | Aixin + Shaun
| Bootstrap Module (Zip uploads) | 60 | 125 | 0.48 | Overrun | 65 | Aixin + Shaun
| Bootstrap Module (Zip uploads) | 60 | 51 | 1.18 | Okay | -9 | Aixin + Shaun
| Integrate Login and Bootstrap Functionalities | 180 | 190 | 0.95 | Okay | 10 | Benjamin + Yiyi
| Debug Login and UI | 120 | 114 | 1.05 | Okay | -6 | Benjamin + Yiyi
| Debug Bootstrap and Updating Bug Metrics | 120 | 125 | 0.96 | Okay | 5 | Aixin + Shaun
| Debug Bootstrap and Updating Bug Metrics | 60 | 58 | 1.03 | Okay | -2 | Aixin + Shaun | 1.4458
| Debug Bootstrap and Updating Bug Metrics | 120 | 130 | 0.92 | Okay | 10 | Aixin + Shaun | 1.1429
0.98765
0.99174
Iteration 1 - Breakdown According to Specific Task | [7 empty] | 1.0448
Iteration | Task Description | Planned Duration (min) | Actual Duration (min) | Value/Score | Overrun/Underrun | Minutes Overrun/Underrun | Coders | 0.98039
1 | Login module - Full functionality | 120 | 83 | 1.45 | Okay | -37 | Benjamin + Yiyi | 0.97166
| Set up database schema, tables and JDBC connection | 120 | 105 | 1.14 | Okay | -15 | Benjamin + Yiyi | 0.64516
| Bootstrap Module (Individual Uploads, Admin Panel, Validation Servlet) | 300 | 304 | 0.99 | Okay | 4 | Aixin + Shaun | 0.78947
| UI Framework (Login, Main page, Admin Panel, other links) using Twitter Bootstrap | 300 | 294 | 1.02 | Okay | -6 | Benjamin + Yiyi | 0.87591
| Bootstrap Module (Zip uploads) | 180 | 297 | 0.61 | Okay | 117 | Aixin + Shaun | 0.99174
| Integrate Login and Bootstrap Functionalities | 180 | 190 | 0.95 | Okay | 10 | Benjamin + Yiyi | 0.94737
| Debug Login and UI | 300 | 114 | 2.63 | Underrun | -186 | Benjamin + Yiyi | 0.97297
| Debug Bootstrap and Updating Bug Metrics | 300 | 313.2 | 0.96 | Okay | 13.2 | Aixin + Shaun | 0.98361
1.0101
1
Iteration 2 - Breakdown According to Specific Coding (PPLOG) Task | [7 empty] | 1.0687
Iteration | Task Description | Planned Duration (min) | Actual Duration (min) | Value/Score | Overrun/Underrun | Minutes Overrun/Underrun | Coders | 1
2 | Heatmap full functionality | 120 | 122 | 0.98 | Okay | 2 | Aixin + Shaun | 0.99174
| Basic Location Report Part 1 | 120 | 121 | 0.99 | Okay | 1 | Benjamin + Ranon | 0.99174
| Heatmap full functionality | 120 | 121 | 0.99 | Okay | 1 | Aixin + Shaun | 1.2245
| Basic Location Report Part 1 | 180 | 192 | 0.94 | Okay | 12 | Benjamin + Ranon | 0.97561
| Basic Location Report Part 2 | 180 | 183 | 0.98 | Okay | 3 | Aixin + Shaun | 0.90566
| Basic Location Report Part 1 | 60 | 75 | 0.8 | Okay | 15 | Benjamin + Ranon | 0.54795
| Basic Location Report Part 1 | 60 | 63 | 0.95 | Okay | 3 | Benjamin + Ranon
| Basic Location Report Part 2 | 60 | 61 | 0.98 | Okay | 1 | Aixin + Shaun
| Basic Location Report Part 3 | 60 | 65 | 0.92 | Okay | 5 | Aixin + Shaun
| Basic Location Report Part 1 | 60 | 64 | 0.94 | Okay | 4 | Benjamin + Ranon
| Basic Location Report Part 4 | 120 | 120 | 1 | Okay | 0 | Benjamin + Ranon
| Basic Location Report Part 3 | 120 | 124 | 0.97 | Okay | 4 | Aixin + Shaun
| Revert coding changes made in revision 68 | 30 | 32 | 0.94 | Okay | 2 | Benjamin + Ranon
| Basic Location Report Part 3 | 90 | 90 | 1 | Okay | 0 | Aixin + Shaun
| Basic Location Report Part 4 | 90 | 91 | 0.99 | Okay | 1 | Benjamin + Ranon
| Basic Location Report Part 4 | 150 | 148 | 1.01 | Okay | -2 | Benjamin + Ranon
| Basic Location Report Part 3 | 90 | 92 | 0.98 | Okay | 2 | Aixin + Shaun
| Basic Location Report Part 4 | 120 | 323 | 0.37 | Overrun | 203 | Benjamin + Ranon
| Basic Location Report Part 3 | 150 | 157 | 0.96 | Okay | 7 | Aixin + Shaun
| Basic Location Report Part 3 | 15 | 17 | 0.88 | Okay | 2 | Aixin + Shaun
| Integrate with earlier functionalities | 120 | 129 | 0.93 | Okay | 9 | Aixin + Shaun
| Integrate with earlier functionalities | 15 | 17 | 0.88 | Okay | 2 | Aixin + Shaun
| Fixing critical bug from BLR Part 1 | 150 | 154 | 0.97 | Okay | 4 | Benjamin + Ranon
| Debugging pair 1 functionality | 180 | 161 | 1.12 | Okay | -19 | Aixin + Shaun
| Debugging pair 2 functionality | 180 | 186 | 0.97 | Okay | 6 | Benjamin + Ranon
| Implement code changes made in revision 68 and further bugs upon redeployment | 15 | 18 | 0.83 | Okay | 3 | Benjamin + Ranon
Iteration 2 - Breakdown According to Specific Task
Iteration | Task Description | Planned Duration (min) | Actual Duration (min) | Value/Score | Overrun/Underrun | Minutes Overrun/Underrun | Coders
2 | Heatmap full functionality | 240 | 243 | 0.99 | Okay | 3 | Aixin + Shaun
| Revert code changes made in revision 68 | 30 | 31.8 | 0.94 | Okay | 1.8 | Ranon
| Basic Location Report Part 1 | 480 | 515 | 0.93 | Okay | 35 | Benjamin + Ranon
| Basic Location Report Part 2 | 240 | 244 | 0.98 | Okay | 4 | Aixin + Shaun
| Basic Location Report Part 3 | 525 | 545 | 0.96 | Okay | 20 | Aixin + Shaun
| Basic Location Report Part 4 | 480 | 682 | 0.7 | Okay | 202 | Benjamin + Ranon
| Integrate with earlier functionalities | 135 | 146 | 0.92 | Okay | 11 | Aixin + Shaun
| Debugging pair 1 functionality | 180 | 161 | 1.12 | Okay | -19 | Aixin + Shaun
| Debugging pair 2 functionality | 345 | 358 | 0.96 | Okay | 13 | Benjamin + Ranon
| Fixing critical bug from BLR part 1 | 180 | 184.2 | 0.98 | Okay | 4.2 | Benjamin + Ranon
| Implement code changes made in revision 68 and further bugs upon deployment | 18 | 18 | 1 | Okay | 0 | Benjamin + Ranon
Iteration 3 - Breakdown According to Specific Coding (PPLOG) Task
Iteration | Task Description | Planned Duration (min) | Actual Duration (min) | Value/Score | Overrun/Underrun | Minutes Overrun/Underrun | Coders
3 | Develop JSON for Authentication and Heatmap | 120 | 121 | 0.99 | Okay | 1 | Ranon + Shaun
| Automatic Group Detection Frontend (UI) and Validation | 210 | 201 | 1.04 | Okay | -9 | Benjamin + YiYi
| Adhoc UI implementation based on feedback | 60 | 61 | 0.98 | Okay | 1 | Benjamin + YiYi
| Develop JSON for Basic Location Report | 120 | 125 | 0.96 | Okay | 5 | Ranon + Shaun
| Develop JSON for Basic Location Report | 120 | 122 | 0.98 | Okay | 2 | Ranon + Shaun
| Automatic Group Detection Backend (Logic + Query) | 180 | 176 | 1.02 | Okay | -4 | Benjamin + YiYi
| Automatic Group Detection Backend (Logic + Query) | 210 | 199 | 1.06 | Okay | -11 | Benjamin + YiYi
| Adhoc fixing of UI and bugs for Heuristic | 60 | 77 | 0.78 | Okay | 17 | Ranon + YiYi
| Adhoc fixing of UI and bugs for Heuristic | 15 | 16 | 0.94 | Okay | 1 | Ranon + YiYi
| Develop JSON for Bootstrap | 90 | 88 | 1.02 | Okay | -2 | Ranon + Shaun
| Develop JSON for Bootstrap | 90 | 91 | 0.99 | Okay | 1 | Ranon + Shaun
| Develop JSON for Bootstrap | 60 | 64 | 0.94 | Okay | 4 | Ranon + Shaun
| Automatic Group Detection Backend (Logic + Query) | 120 | 116 | 1.03 | Okay | -4 | Benjamin + YiYi
| Automatic Group Detection Backend (Logic + Query) | 120 | 180 | 0.67 | Okay | 60 | Benjamin + YiYi
| Develop JSON for Bootstrap | 30 | 31 | 0.97 | Okay | 1 | Ranon + Shaun
| Automatic Group Detection Backend (Logic + Query) | 120 | 116 | 1.03 | Okay | -4 | Benjamin + YiYi
| Debugging of JSON errors | 180 | 190 | 0.95 | Okay | 10 | Ranon + Shaun
| Integrate with earlier functionalities | 120 | 121 | 0.99 | Okay | 1 | Shaun + YiYi
| Debugging of Automatic Group Detection | 90 | 89 | 1.01 | Okay | -1 | Shaun + YiYi
| Debugging of Automatic Group Detection | 90 | 96 | 0.94 | Okay | 6 | Shaun + YiYi
Iteration 3 - Breakdown According to Specific Task
Iteration | Task Description | Planned Duration (min) | Actual Duration (min) | Value/Score | Overrun/Underrun | Minutes Overrun/Underrun | Coders
3 | Develop JSON for Authentication and Heatmap | 120 | 121 | 0.99 | Okay | 1 | Ranon + Shaun
| Automatic Group Detection Frontend (UI) and Validation | 210 | 201 | 1.04 | Okay | -9 | Benjamin + YiYi
| Adhoc UI implementation based on feedback | 60 | 61.2 | 0.98 | Okay | 1.2 | Benjamin + YiYi
| Develop JSON for Basic Location Report | 240 | 247 | 0.97 | Okay | 7 | Ranon + Shaun
| Adhoc Fixing of UI and Bugs for Heuristics | 60 | 93 | 0.65 | Okay | 33 | Ranon + Shaun
| Automatic Group Detection Backend | 780 | 988 | 0.79 | Okay | 208 | Benjamin + YiYi
| Develop JSON for Bootstrap | 240 | 274 | 0.88 | Okay | 34 | Ranon + Shaun
| Integrate with earlier functionalities | 120 | 121 | 0.99 | Okay | 1 | Shaun + YiYi
| Debugging of JSON errors | 180 | 190 | 0.95 | Okay | 10 | Ranon + Shaun
| Debugging of Automatic Group Detection | 180 | 185 | 0.97 | Okay | 5 | Shaun + YiYi
Iteration 4 - Breakdown According to Specific Coding (PPLOG) Task
Iteration | Task Description | Planned Duration (min) | Actual Duration (min) | Value/Score | Overrun/Underrun | Minutes Overrun/Underrun | Coders
4 | Group Report Top-K Next Places Frontend + Validation | 120 | 122 | 0.98 | Okay | 2 | Ranon + Shaun
| Group Report Top K Popular Places Frontend and Validation | 120 | 119 | 1.01 | Okay | -1 | Aixin + YiYi
| Develop JSON for Automatic Group Detection | 120 | 120 | 1 | Okay | 0 | Aixin + YiYi
| Group Report Top-K Next Places (Query + Logic) | 180 | 185 | 0.97 | Okay | 5 | Ranon + Shaun
| Group Report Top K Popular Places Backend(Query + Logic ) | 120 | 120 | 1 | Okay | 0 | Aixin + YiYi
| Group Report Top K Popular Places Backend(Query + Logic ) | 120 | 120 | 1 | Okay | 0 | Aixin + YiYi
| Group Report Top K Popular Places Backend(Query + Logic ) | 120 | 120 | 1 | Okay | 0 | Aixin + YiYi
| Group Report Top-K Next Places (Query + Logic) | 30 | 44 | 0.68 | Okay | 14 | Ranon + Shaun
| Group Report Top-K Next Places (JSON) | 60 | 62 | 0.97 | Okay | 2 | Ranon + Shaun
| Group Report Top-K Next Places (Query + Logic) | 180 | 164 | 1.1 | Okay | -16 | Ranon + Shaun
| Group Report Top K Popular Places Backend(JSON ) | 120 | 121 | 0.99 | Okay | 1 | Aixin + YiYi
| Group Report Top-K Next Places (JSON) | 60 | 59 | 1.02 | Okay | -1 | Ranon + Shaun
| Make minor changes related to Heuristic Evaluation feedback | 15 | 4 | 3.75 | Underrun | -11 | Ranon + Shaun
| Make minor changes related to Heuristic Evaluation feedback | 120 | 94 | 1.28 | Okay | -26 | Ranon + Shaun
| Integrate with earlier functionalities | 120 | 126 | 0.95 | Okay | 6 | Aixin + YiYi
| Integrate with earlier functionalities | 120 | 120 | 1 | Okay | 0 | Aixin + YiYi
| Debugging of Group location Next Places | 90 | 99 | 0.91 | Okay | 9 | Ranon + Shaun
| Debugging of AGD JSON + Group location Popular Places | 120 | 144 | 0.83 | Okay | 24 | Aixin + YiYi
| Debugging of AGD JSON + Group location Popular Places | 120 | 135 | 0.89 | Okay | 15 | Aixin + YiYi
| Debugging of AGD JSON + Group location Popular Places | 120 | 147 | 0.82 | Okay | 27 | Aixin + YiYi
| Debugging of AGD JSON + Group location Popular Places | 15 | 12 | 1.25 | Okay | -3 | Aixin + YiYi
| Debugging of Group location Next Places | 120 | 144 | 0.83 | Okay | 24 | Ranon + Shaun
| Debugging of Group location Next Places | 45 | 21 | 2.14 | Underrun | -24 | Ranon + Shaun
| Debugging of Group location Next Places | 15 | 1 | 15 | Underrun | -14 | Ranon + Shaun
Iteration 4 - Breakdown According to Specific Task
Iteration | Task Description | Planned Duration (min) | Actual Duration (min) | Value/Score | Overrun/Underrun | Minutes Overrun/Underrun | Coders
4 | Group Report Top-K Next Places Frontend + Validation | 120 | 122 | 0.98 | Okay | 2 | Ranon + Shaun
| Group Report Top-K Popular Places Frontend + Validation | 120 | 118.8 | 1.0101 | Okay | -1.2 | Aixin + YiYi
| Develop JSON for Automatic Group Detection | 120 | 120 | 1 | Okay | 0 | Aixin + YiYi
| Group Report Top-K Next Places (Query + Logic) | 420 | 393 | 1.07 | Okay | -27 | Ranon + Shaun
| Group Report Top K Popular Places Backend(Query + Logic ) | 360 | 360 | 1 | Okay | 0 | Aixin + YiYi
| Group Report Top-K Next Places (JSON) | 120 | 121 | 0.99 | Okay | 1 | Ranon + Shaun
| Group Report Top K Popular Places Backend(JSON ) | 120 | 121 | 0.99 | Okay | 1 | Aixin + YiYi
| Make minor changes related to Heuristic Evaluation feedback | 120 | 98 | 1.22 | Okay | -22 | Aixin + YiYi
| Integrate with earlier functionalities | 240 | 246 | 0.98 | Okay | 6 | Ranon + Shaun
| Debugging of Group location Next Places | 240 | 265 | 0.91 | Okay | 25 | Ranon + Shaun
| Debugging of AGD JSON + Group location Popular Places | 240 | 438 | 0.55 | Okay | 198 | Aixin + YiYi
Iteration 5 - Breakdown According to Specific Coding (PPLOG) Task
Iteration | Task Description | Planned Duration (min) | Actual Duration (min) | Value/Score | Overrun/Underrun | Minutes Overrun/Underrun | Coders
5 | Implementing Graphical Display for Heatmap | 120 | 131 | 0.92 | Okay | 11 | Aixin + Benjamin
| Implement changes to general UI look based on Heuristic Feedback | 120 | 123 | 0.98 | Okay | 3 | Ranon + Yiyi
| Implementing Graphical Display for Heatmap | 120 | 112 | 1.07 | Okay | -8 | Aixin + Benjamin
| Implement changes to general UI look based on Heuristic Feedback | 120 | 124 | 0.97 | Okay | 4 | Ranon + Yiyi
| Implement changes to general UI look based on Heuristic Feedback | 120 | 154 | 0.78 | Okay | 34 | Ranon + Yiyi
| Implementing Graphical Display for Heatmap | 180 | 203 | 0.89 | Okay | 23 | Aixin + Benjamin
| Implement changes to general UI look based on Heuristic Feedback | 15 | 14 | 1.07 | Okay | -1 | Ranon + Yiyi
| Implement changes to UI based on Supervisor Feedback | 120 | 122 | 0.98 | Okay | 2 | Ranon + Yiyi
| Implement changes to UI based on Supervisor Feedback | 60 | 103 | 0.58 | Okay | 43 | Ranon + Yiyi
| Implementing Date and Time picker | 60 | 64 | 0.94 | Okay | 4 | Aixin + Benjamin
| Debug Issues from UAT for Basic Reports, Bootstrap and Heatmap | 60 | 59 | 1.02 | Okay | -1 | Ranon + Yiyi
| Debug Issues from UAT for Basic Reports, Bootstrap and Heatmap | 180 | 196 | 0.92 | Okay | 16 | Ranon + Yiyi
| Debug Issues from UAT for Login, Heatmap, Automatic Group Detection, and Group Report | 105 | 108 | 0.97 | Okay | 3 | Aixin + Benjamin
| Debug Issues from UAT for Login, Heatmap, Automatic Group Detection, and Group Report | 135 | 160 | 0.84 | Okay | 25 | Aixin + Benjamin
| Implementing Date and Time picker | 90 | 102 | 0.88 | Okay | 12 | Aixin + Benjamin
| Debug integrated functionalities | 120 | 147 | 0.82 | Okay | 27 | Ranon + Yiyi
| Code Commenting and Javadoc generation | 120 | 118 | 1.02 | Okay | -2 | Aixin + Benjamin
| Code Commenting and Javadoc generation | 15 | 14 | 1.07 | Okay | -1 | Aixin + Benjamin
| Debug integrated functionalities | 15 | 21 | 0.71 | Okay | 6 | Ranon + Yiyi
| Debug integrated functionalities | 45 | 73 | 0.62 | Okay | 28 | Ranon + Yiyi
| Debug integrated functionalities | 15 | 11 | 1.36 | Okay | -4 | Ranon + Yiyi
| Debug integrated functionalities | 15 | 11 | 1.36 | Okay | -4 | Ranon + Yiyi
Iteration 5 - Breakdown According to Specific Task
Iteration | Task Description | Planned Duration (min) | Actual Duration (min) | Value/Score | Overrun/Underrun | Minutes Overrun/Underrun | Coders
5 | Implement changes to general UI look based on Heuristic Feedback | 360 | 415 | 0.87 | Okay | 55 | Aixin + Benjamin
| Implementing Graphical Display for Heatmap | 420 | 446 | 0.94 | Okay | 26 | Ranon + Yiyi
| Implementing Date and Time picker | 180 | 166 | 1.08 | Okay | -14 | Aixin + Benjamin
| Implement changes to UI based on Supervisor Feedback | 180 | 225 | 0.8 | Okay | 45 | Ranon + Yiyi
| Debug Issues from UAT for Basic Reports, Bootstrap and Heatmap | 240 | 255 | 0.94 | Okay | 15 | Ranon + Yiyi
| Debug Issues from UAT for Login, Heatmap, Automatic Group Detection, and Group Report | 240 | 268 | 0.9 | Okay | 28 | Aixin + Benjamin
| Code Commenting and Javadoc generation | 120 | 132 | 0.91 | Okay | 12 | Aixin + Benjamin
| Debug integrated functionalities | 120 | 263 | 0.46 | Overrrun | 143 | Ranon + Yiyi

## Graph
Login module - Full functionality | Login module - Full functionality | 1.45
Set up database schema, tables and JDBC connection | Set up database schema, tables and JDBC connection | 1.14
Login module - Full functionality | Login module - Full functionality | #REF!
Bootstrap Module (Individual Uploads, Admin Panel, Validation Servlet) | Bootstrap Module (Individual Uploads, Admin Panel, Validation Servlet) | 0.99
UI Framework (Login, Main page, Admin Panel, other links) using Twitter Bootstrap | Bootstrap Module (Individual Uploads, Admin Panel, Validation Servlet) | #REF!
Integrate Login and Bootstrap Functionalities | UI Framework (Login, Main page, Admin Panel, other links) using Twitter Bootstrap | 1.02
Debug Login and UI | Bootstrap Module (Zip uploads) | 0.61
Debug Bootstrap and Updating Bug Metrics | Bootstrap Module (Zip uploads) | #REF!
| Bootstrap Module (Zip uploads) | #REF!
| Integrate Login and Bootstrap Functionalities | 0.95
| Debug Login and UI | 2.63
| Debug Bootstrap and Updating Bug Metrics | 0.96
| Debug Bootstrap and Updating Bug Metrics | #REF!
| Debug Bootstrap and Updating Bug Metrics | #REF!
| Heatmap full functionality | 0.98
| Basic Location Report Part 1 | 0.99
| Heatmap full functionality | 0.99
| Basic Location Report Part 1 | 0.94
| Basic Location Report Part 2 | 0.98
| Basic Location Report Part 1 | 0.8
| Basic Location Report Part 1 | 0.95
| Basic Location Report Part 2 | 0.98
| Basic Location Report Part 3 | 0.92
| Basic Location Report Part 1 | 0.94
| Basic Location Report Part 4 | 1
| Basic Location Report Part 3 | 0.97
| Revert coding changes made in revision 68 | 0.94
| Basic Location Report Part 3 | 1
| Basic Location Report Part 4 | 0.99
| Basic Location Report Part 4 | 1.01
| Basic Location Report Part 3 | 0.98
| Basic Location Report Part 4 | 0.37
| Basic Location Report Part 3 | 0.96
| Basic Location Report Part 3 | 0.88
| Integrate with earlier functionalities | 0.93
| Integrate with earlier functionalities | 0.88
| Fixing critical bug from BLR Part 1 | 0.97
| Debugging pair 1 functionality | 1.12
| Debugging pair 2 functionality | 0.97
| Implement code changes made in revision 68 and further bugs upon redeployment | 0.83
| Heatmap full functionality | 0.99
| Basic Location Report Part 1 | 0.93
| Basic Location Report Part 2 | 0.98
| Basic Location Report Part 3 | 0.96
| Basic Location Report Part 4 | 0.7
| Integrate with earlier functionalities | 0.92
| Debugging pair 1 functionality | 1.12
| Debugging pair 2 functionality | 0.96
| Develop JSON for Authentication and Heatmap | 0.99
| Automatic Group Detection Frontend (UI) and Validation | 1.04
| Adhoc UI implementation based on feedback | 0.98
| Develop JSON for Basic Location Report | 0.96
| Develop JSON for Basic Location Report | 0.98
| Automatic Group Detection Backend (Logic + Query) | 1.02
| Automatic Group Detection Backend (Logic + Query) | 1.06
| Adhoc fixing of UI and bugs for Heuristic | 0.78
| Adhoc fixing of UI and bugs for Heuristic | 0.94
| Develop JSON for Bootstrap | 1.02
| Develop JSON for Bootstrap | 0.99
| Develop JSON for Bootstrap | 0.94
| Automatic Group Detection Backend (Logic + Query) | 1.03
| Automatic Group Detection Backend (Logic + Query) | 0.67
| Develop JSON for Bootstrap | 0.97
| Automatic Group Detection Backend (Logic + Query) | 1.03
| Debugging of JSON errors | 0.95
| Integrate with earlier functionalities | 0.99
| Debugging of Automatic Group Detection | 1.01
| Debugging of Automatic Group Detection | 0.94
| Develop JSON for Authentication and Heatmap | 0.99
| Automatic Group Detection | 0.79
| Develop JSON for Basic Location Report | 0.97
| Develop JSON for Bootstrap | 0.88
| Integrate with earlier functionalities | 0.99
| Debugging of JSON errors | 0.95
| Debugging of Automatic Group Detection | 0.97
| Group Report Top-K Next Places Frontend + Validation | 0.98
| Group Report Top K Popular Places Frontend and Validation | 1.01
| Develop JSON for Automatic Group Detection | 1
| Group Report Top-K Next Places (Query + Logic) | 0.97
| Group Report Top K Popular Places Backend(Query + Logic ) | 1
| Group Report Top K Popular Places Backend(Query + Logic ) | 1
| Group Report Top K Popular Places Backend(Query + Logic ) | 1
| Group Report Top-K Next Places (Query + Logic) | 0.68
| Group Report Top-K Next Places (JSON) | 0.97
| Group Report Top-K Next Places (Query + Logic) | 1.1
| Group Report Top K Popular Places Backend(JSON ) | 0.99
| Group Report Top-K Next Places (JSON) | 1.02
| Make minor changes related to Heuristic Evaluation feedback | 3.75
| Make minor changes related to Heuristic Evaluation feedback | 1.28
| Integrate with earlier functionalities | 0.95
| Integrate with earlier functionalities | 1
| Debugging of Group location Next Places | 0.91
| Debugging of AGD JSON + Group location Popular Places | 0.83
| Debugging of AGD JSON + Group location Popular Places | 0.89
| Debugging of AGD JSON + Group location Popular Places | 0.82
| Debugging of AGD JSON + Group location Popular Places | 1.25
| Debugging of Group location Next Places | 0.83
| Debugging of Group location Next Places | 2.14
| Debugging of Group location Next Places | 15
| Group Report Top-K Next Places Frontend + Validation | 0.98
| Develop JSON for Automatic Group Detection | 1
| Group Report Top-K Next Places (Query + Logic) | 1.07
| Group Report Top K Popular Places Backend(Query + Logic ) | 1
| Group Report Top-K Next Places (JSON) | 0.99
| Group Report Top K Popular Places Backend(JSON ) | 0.99
| Make minor changes related to Heuristic Evaluation feedback | 1.22
| Integrate with earlier functionalities | 0.98
| Debugging of Group location Next Places | 0.91
| Debugging of AGD JSON + Group location Popular Places | 0.55