## Sheet1
Iteration 1 | (In Days) |  | (In Hours) |  | Metric Score (Planned / Actual) % Days | Metric Score (Planned / Actual) % Hours | Mitigation Action(s)
| Planned | Actual | Planned | Actual
TOTAL | Duration |  | 76.5 | 75.5 | 1.0357 | 1.0132
| Aug 24 - Sep 21 | Aug 24 - Sep 20
Work Days
| 29 | 28
Iteration 2 | (In Days) |  | (In Hours) |  | Metric Score (Planned / Actual) % Days | Metric Score (Planned / Actual) % Hours
| Planned | Actual | Planned | Actual
TOTAL | Duration |  | 64 | 69.4 | 1 | 0.92219
| Sep 22 - Oct 7 | Sep 22 - Oct 7
Work Days
| 16 | 16
[8 empty] | Iteration | Planned Hours | Actual Hours | Score | Planned Days | Actual Days | Percentage completed
[8 empty] | Iteration 1 | 76.5 | 75.5 | 101.3% | 29 | 28 | 103.6%
[8 empty] | Iteration 2 | 64 | 69.4 | 92.22% | 16 | 16 | 100%
Iteration 3 | (In Days) |  | (In Hours) |  | Metric Score (Planned / Actual) % Days | Metric Score (Planned / Actual) % Hours |  | Iteration 3 | 60 | 66.1 | 90.77% | 13 | 15 | 86.67%
| Planned | Actual | Planned | Actual |  |  |  | Iteration 4 | 70.5 | 75.5 | 93.38% | 11 | 13 | 84.62%
TOTAL | Duration |  | 60 | 66.1 | 0.86667 | 0.90772 |  | Iteration 5 | 54.5 | 54.8 | 99.45% | 14 | 14 | 100%
| 7 Oct - 19 Oct | 7 Oct - 21 Oct
[8 empty] | Iteration | Hours Completd | Days Completed | 3 | 4 | 5 | 6
| Work Days | [6 empty] | 1 | 101.3% | 103.6% | 95.74% | 101.3% | 99.45% | 97.56%
| 13 | 15 | [5 empty] | 2 | 92.22% | 100%
[8 empty] | 3 | 90.77% | 86.67%
[8 empty] | 4 | 93.38% | 84.62%
[8 empty] | 5 | 99.45% | 100%
Iteration 4 | (In Days) |  | (In Hours) |  | Metric Score (Planned / Actual) % Days | Metric Score (Planned / Actual) % Hours
| Planned | Actual | Planned | Actual
TOTAL | Duration |  | 70.5 | 75.5 | 0.84615 | 0.93377
| Oct 21 - Nov 1 | Oct 21 - Nov 2
Work Days
| 11 | 13
Iteration 5 | (In Days) |  | (In Hours) |  | Metric Score (Planned / Actual) % Days | Metric Score (Planned / Actual) % Hours
| Planned | Actual | Planned | Actual
TOTAL | Duration |  | 62.5 | 63.8 | 1 | 97.9624
| Nov 3 - Nov 16 | Nov 3 - Nov 16
Work Days
| 14 | 14
Remarks (Reason for Low Metric Score) : 1) Unfamiliar with the usage of PPlog and Project Schedule on Violet
2) Predictions of certain task requirements and timing were not accurate
Mitigation Action: 1) Met up with supervisor and checked the forums for similar issues on how to plan for each iteration
2) Used the mistakes made from iteration 1 to plan the pplogs and schedule for the future iterations more carefully.
Remarks (Reason for Low Metric Score) : 1) Underestimate the time need for some events, like lab test and PM review Those event disperse some energy and take more time than we thought.
Mitigation Action: 1) Including the big event in plan
2) Used the mistakes made from iteration 2 to plan the pplogs and schedule for the future iterations more carefully.
Remarks (Reason for Low Metric Score) : 1) Main Challenge: Our understanding of the Group Detection functionality was not as complete as we had previously believed. We needed time to consider corner cases and develop a solution. Hence, this posed a challenge in meeting the planned schedule of 8.5 hours.
Mitigation Action: 1) Request for 1 day extension of this iteration with the possibility of additional days as required from our supervisor .
2) Once the task was finished, adjusted schedule according to the number of additional days taken by drawing from buffer period (2 days)
3) Used the mistakes made from iteration 3 to plan the pplogs and schedule for the future iterations more carefully. In particular, looked at and ensured coding tasks are spread out over enough time.
Remarks : 1) Metric score within safe range, however there are no buffer days remaining to mitigate the 1 day overrun.
Mitigation Action: 1) Informed supervisor of overrun, in particular to indicate lack of buffer days availible to cover the overrun despite the safe SM score.
2) Consider rescoping of iteration 5 tasks to mitigate overrun
Remarks : 1) Metric score within safe range.
Mitigation Action: None required