## Slide 1: Supervisor Meeting 1
G4T7
Aixin Benjamin Ranon Shaun Yiyi

## Slide 2: Agenda
Roles & Responsibilities
Key Metrics
Iteration 1 Progress Review
Iteration 2 Updates

## Slide 3: Roles – Iteration 1
Task | Pair Programmers | Project Manager
Log in/out UI | Benjamin, Yiyi | Ranon
Bootstrap | Shaun, Aixin | 

## Slide 4: Schedule Metrics
Iteration 1 | (In Days) |  | (In Hours) |  | Metric Score (Planned/Actual Hours) %
 | Planned | Actual | Planned | Actual | 
Research | 11 | 11 | 27 | 27.4 | 98.69281046
Design | 2 | 2 | 7 | 7.2 | 
Coding | 3 | 4 | 17 | 18.1 | 
Integration | 2 | 1 | 3 | 3.2 | 
Deployment | 1 | 1 | 2.5 | 2.2 | 
Testing | 1 | 1 | 3 | 3 | 
Debugging | 3 | 5 | 10 | 7.1 | 
Progress Review | 3 | 3 | 7 | 7.3 | 
NVD3 Library | 2 | Postponed | 6 | Postponed | 
TOTAL | 26 | 28 | 76.5 | 75.5 | 

## Slide 5: Schedule Metrics
Chart: 
| Research | Design | Coding | Integration | Deployment | Testing | Debugging | Progress Review
(In Hours) Planned | 27 | 7 | 17 | 3 | 2.5 | 3 | 10 | 7
(In Hours) Actual | 27.4 | 7.2 | 18.1 | 3.2 | 2.2 | 3 | 7.1 | 7.3

## Slide 6: Schedule Metrics
Chart: 
| Research | Design | Coding | Integration | Deployment | Testing | Debugging | Progress Review
(In Days) Planned | 11 | 2 | 3 | 2 | 1 | 1 | 3 | 3
(In Days) Actual | 11 | 2 | 4 | 1 | 1 | 1 | 5 | 3

## Slide 7: Schedule Metrics
Chart: 
| Research | Design | Coding | Integration | Deployment | Testing | Debugging | Progress Review
(In Hours) Planned | 27 | 7 | 17 | 3 | 2.5 | 3 | 10 | 7
(In Hours) Actual | 27.4 | 7.2 | 18.1 | 3.2 | 2.2 | 3 | 7.1 | 7.3
Chart: 
| Research | Design | Coding | Integration | Deployment | Testing | Debugging | Progress Review
(In Hours) Actual | 27.4 | 7.2 | 18.1 | 3.2 | 2.2 | 3 | 7.1 | 7.3

## Slide 8: Iteration 1 PPLog Metrics
Task Description | Planned Duration (min) | Actual Duration (min) | Value/Score | Overrun/Underrun | Minutes Overrun/Underrun | Coders
Login module - Full functionality | 45 | 34 | 0.755555556 | Underrun | -11 | Benjamin + Yiyi
Set up database schema, tables and JDBC connection | 120 | 105 | 0.875 | Underrun | -15 | Benjamin + Yiyi
Login module - Full functionality | 75 | 49 | 0.653333333 | Underrun | -26 | Benjamin + Yiyi
UI Framework (Login, Main page, Admin Panel, other links) using Twitter Bootstrap | 300 | 294 | 0.98 | Underrun | -6 | Benjamin + Yiyi
Integrate Login and Bootstrap Functionalities | 180 | 190 | 1.055555556 | Overrun | 10 | Benjamin + Yiyi
Debug Login and UI | 120 | 114 | 0.95 | Underrun | -6 | Benjamin + Yiyi

## Slide 9: Iteration 1 PPLog Metrics
Task Description | Planned Duration (min) | Actual Duration (min) | Value/Score | Overrun/Underrun | Minutes Overrun/Underrun | Coders
Bootstrap Module (Individual Uploads, Admin Panel, Validation Servlet) | 120 | 123 | 1.025 | Overrun | 3 | Aixin + Shaun
Bootstrap Module (Individual Uploads, Admin Panel, Validation Servlet) | 180 | 181 | 1.005555556 | Overrun | 1 | Aixin + Shaun
Bootstrap Module (Individual Uploads, Admin Panel, Validation Servlet) | 120 | 123 | 1.025 | Overrun | 3 | Aixin + Shaun
Bootstrap Module (Zip uploads) | 120 | 121 | 1.008333333 | Overrun | 1 | Aixin + Shaun
Bootstrap Module (Zip uploads) | 60 | 125 | 2.083333333 | Overrun | 65 | Aixin + Shaun
Bootstrap Module (Zip uploads) | 60 | 51 | 0.85 | Underrun | -9 | Aixin + Shaun
Debug Bootstrap and Updating Bug Metrics | 120 | 125 | 1.041666667 | Overrun | 5 | Aixin + Shaun
Debug Bootstrap and Updating Bug Metrics | 60 | 58 | 0.966666667 | Underrun | -2 | Aixin + Shaun
Debug Bootstrap and Updating Bug Metrics | 120 | 130 | 1.083333333 | Overrun | 10 | Aixin + Shaun

## Slide 10: Bug Metrics
S/N | Iteration | Bug Description | Bug Severity | Function Affected | Mitigation Plan | Status
1 | 1 | User is able to access application pages via direct URL even after logging out. | Medium | Application Login | To be fixed during debugging (14th Sept) | Resolved
2 | 1 | Faulty Admin Page Validation where Admin does not have to validate password before entering the panel | Medium | Access to Admin Panel for Bootstrap / Upload | To be fixed during debugging (14th Sept) | Resolved
3 | 1 | Faulty Admin Panel session management whereby admin booted out of admin panel upon uploading/bootstrapping | Medium | Access to Admin Panel for Bootstrap / Upload | To be fixed during debugging (15-16th Sept) | Resolved
4 | 1 | Application does not reject duplicated mac_addresses when uploaded from demographics.csv | Medium | Bootstrap Data validation | To be fixed during debugging (15-16th Sept) | Resolved
5 | 1 | Application does not currently detect or correct duplicate rows in the location.csv entries | Medium | Bootstrap Data validation | To be fixed during debugging (15-16th Sept) | Resolved
6 | 1 | Output displays error on multiple rows for a specific line validated instead of all on the same line | Low | Bootstrap Result Display | To be fixed during debugging (15-16th Sept) | Resolved
Notes: Ranon’s bug we should fix in interation 2

## Slide 11: PM – related Challenges
Untimely commit of deliverables on Subversion (SVN)
Uncertainty on dealing with tasks requiring extensions –e.g. debugging task
Others

## Slide 12: Coding – related Challenges
Underestimated time required for Bootstrap
  Unit Testing Data too large
Different Research Materials used
Unstandardized Coding Conventions
Uncertainty of the documentation of bugs and test cases

## Slide 13: Action Plan
PM to enforce regular and timely commits of deliverables
Everyone to standardize indentation and coding (format)
Open communication amongst the team to standardize all resources before coding

## Slide 14: Action Plan
Conduct team-level design analysis to spot potential bottlenecks
Ensure that coding-related commits happen ONLY during a coding session
Pair coders is to reflect the need for time extension and inform the PM
Both pairs to be responsible to ensure timely commits

## Slide 15: Roles – Iteration 2
Task | Pair Programmers | Project Manager
Basic Location Report: Part 1+4 | Benjamin, Ranon | Yiyi
Heatmap Basic Location Report: Part 2+3 | Shaun, Aixin | 

## Slide 16: Iteration 2- Schedule
Iteration 2 | (In Days) |  | (In Hours) |  | Metric Score (Planned/Actual Hours) %
 | Planned | Actual | Planned | Actual | 
Design of Heatmap | 1 | 1 | 3 | 3 | 1.146496815
Design of Basic Location Report | 1 | 1 | 3 | 3 | 
Heatmap functionality | 2 | 2 | 4 | 4.1 | 
Develop the basic Breakdown by year and gender and school | 4 | 2 | 8 | 5.6 | 
TOTAL | 8 | 6 | 18 | 15.7 | 

## Slide 17: Iteration 2- PPLog
Task Description | Planned Hours | Acutual Hours | Planned Date | Actual Date
Heatmap full functionality | 4 h | 4 h 3 min | 23/9/2014-24/9/2014 | 23/9/2014-24/9/2014
Basic Location Report Part 1: Develop the basic Breakdown by year and gender and school | 8 h | 5 h 13 min | 23/9/2014-26/9/2014 | 23/9/2014-24/9/2014

## Slide 18: Goals and Milestone
Complete Critical task by 1st October
  Basic Location Report : Top-k Next Placess
100% PPLog matches for Iteration 2
Match all PP metric scores to be between 0.8 and 1.5
Minimal documentation delays (1-2 days)

## Slide 19: Critical Path(Total 16 Days)
Design
BLR: Part 4
BLR: Par 1
Supervisor Meeting Preparation
BLR: Part 3
BLR: Part 2
Heatmap
1 Day
PM Review Preparation
Integration
Integration
9 Days

## Slide 20: Critical Path
Testing
1 Day
3 Days
Debugging
Update of documents
1 Day
Update of documents
1 Day