## Slide 1: Supervisor Meeting 3
G4T7
Aixin Benjamin Ranon Shaun Yiyi

## Slide 2: Agenda
Key Metrics
Progress Update
Forging Ahead
Challenges
Mitigation Plans
Summary Recap
Updates from Supervisor Meeting 2

## Slide 3: Response to Supervisor Feedback from Meeting 2
Specific hours for tasks in schedule metrics is unnecessary
  Included only days SM scores into meeting slides
Subversion app directory should not contain auto-generated directories
  Removed “build” and “dist” from app directory
Ordering of UI elements should be lexicographic
  Adapted feedback on PPLog Task 45

## Slide 4: Response to Supervisor Feedback from Meeting 2
Usage of .zip files for backend test data for each functionality
  Combined .zip file has been created and will be maintained
  Committed on SVN Log Task 190
  Located at:
    testing\Test Cases\backend-testCases\backend_merged_SQL.zip

## Slide 5: Progress(Past 2 weeks)
Heuristics Evaluation
Automatic Group Detection
JSON for:
  Authentication
  Bootstrap
  Heatmap
  Basic Location Report:
    Breakdown by Gender, School, Year
    Top-K Popular Places
    Top-K Companions
    Top-K Next Places

## Slide 6: Roles and Responsibilities
Task | Pair Programmers | Project Manager
JSON for: Authentication Bootstrap Heatmap Basic Location Reports | Shaun, Ranon | Ai Xin
Automatic Group Detection | Benjamin, Yiyi | 

## Slide 7: Schedule Metrics
 | Iterations | (In Days) |  | Metric Score (Days) %
 |  | Planned | Actual | 
TOTAL | Iteration 1 | 29 | 28 | 1.04
 | Iteration 2 | 16 | 16 | 1.00
 | Iteration 3 | 13 | 15 | 0.87

## Slide 8: PPLog Metric
Task Description | Planned Duration (hrs) | Actual Duration (hrs) | Score | Status
JSON for Authentication + Heatmap | 2.0 | 2.2 | 1.10 | Okay
JSON for Basic Location Report | 4.0 | 4.1 | 1.03 | Okay
JSON for Bootstrap | 4.0 | 4.6 | 1.14 | Okay
Automatic Group Detection | 13.0 | 16.5 | 1.27 | Okay
Integrate with earlier functionalities | 2.0 | 2.0 | 1.01 | Okay
Debugging JSON errors | 3.0 | 3.2 | 1.06 | Okay
Debugging AGD | 3.0 | 3.1 | 1.03 | Okay

## Slide 9: PPLog Metric
Task Description | Planned Duration (hrs) | Actual Duration (hrs) | Score | Status
JSON for Authentication + Heatmap | 2.0 | 2.2 | 1.10 | Okay
JSON for Basic Location Report | 4.0 | 4.1 | 1.03 | Okay
JSON for Bootstrap | 4.0 | 4.6 | 1.14 | Okay
Automatic Group Detection | 13.0 | 16.5 | 1.27 | Okay
Integrate with earlier functionalities | 2.0 | 2.0 | 1.01 | Okay
Debugging JSON errors | 3.0 | 3.2 | 1.06 | Okay
Debugging AGD | 3.0 | 3.1 | 1.03 | Okay
Notes: Highlighted as the cause for the schedule overrun

## Slide 10: Bug Metrics
BUG SCORE = 34
(4 low, 6 medium)
Bugs were resolved immediately

## Slide 11: Challenges
Pressure to adhere to the schedule without full knowledge of what is expected of the functionality
  AGD affected, consuming 2 more days than expected
Unclear feedback given during Heuristics Evaluation
  Team could not get a full picture of the feedback
Uncertainty on when to deal with feedback given from Heuristics Evaluation

## Slide 12: Mitigation Plans
Lacking full knowledge of what is expected of the functionality
  Decided on one working approach and data structure
  Seek clarifications from Professor Yeow Leong and peers
  Sound off to PM of possible overrun of the task & emailed Supervisor
Unclear feedback given during Heuristics Evaluation
  Clarified doubts with peers
  Debated the importance or relevance of the various feedback
Uncertainty on when to deal with feedback given from Heuristics Evaluation
  Asked for advice from Professor Yeow Leong
    Minutes -> Supervisor -> Minutes 5 (17102014)

## Slide 13: Mitigation Plans
Action plan to deal with schedule overrun
  Request for 1 day extension of this iteration with the possibility of additional days as required from our supervisor .
  Once the task was finished, adjusted schedule according to the number of additional days taken by drawing from buffer period (2 days)
  Used the mistakes made from iteration 3 to plan the pplogs and schedule for the future iterations more carefully. In particular, looked at and ensured coding tasks are spread out over enough time.

## Slide 14: Summary Recap
Iteration 3
  100% PPLog matches for Iteration 3
  Minimal documentation delays
  Keep PP metric scores between 0.8 and 1.5
✔
✔
✔

## Slide 15: Forging Ahead
Milestones
  User Acceptance Test
    Dedicated Test Cases Phase
  Final Presentation
Iteration 4
  Timely end of Iteration 4
    Maintain timely administrative documentation
    Rigorous testing and confirmation of functionalities expected output, particularly with regards to JSON output

## Slide 16: Clarifications
Consistency of PP scores VS PPLog metric scores
Updating of the Heuristics Evaluation feedback
Feedback