## Slide 1: Supervisor Meeting 4
G4T7
Aixin Benjamin Ranon Shaun Yiyi

## Slide 2: Agenda
Key Metrics
Progress Update
Review
Challenges
Updates from Supervisor Meeting 3

## Slide 3: Response to Supervisor Feedback from Meeting 3
Amended Pair Programming Scores to use same calculation method as that on PPLog
Implemented a more comprehensive bug metrics from Iteration 4 onwards
Revamped bug metrics to reflect per-iteration testing instead of per-functionality testing

## Slide 4: Progress(Past 2 weeks)
User Acceptance Test
Group-Aware Location Reports
JSON
  Automatic Group Detection
  Group-Aware Location Reports
Extensive Testing

## Slide 5: Roles and Responsibilities
Task | Pair Programmers | Project Manager
Group-Aware Next Places + JSON | Shaun, Ranon | Benjamin
Group-Aware Popular Places + JSON Automatic Group Detection JSON | Aixin, Yiyi | 

## Slide 6: Schedule Metrics
 | Iterations | (In Days) |  | Metric Score (Days) %
 |  | Planned | Actual | 
TOTAL | Iteration 1 | 29 | 28 | 1.04
 | Iteration 2 | 16 | 16 | 1.00
 | Iteration 3 | 13 | 15 | 0.87
 | Iteration 4 | 12 (11) | 13 | 0.85

## Slide 7: Bug Metrics
BUG SCORE = 51
(6 low, 9 medium)
Bugs were resolved immediately

## Slide 8: PPLog Metric
Task Description | Planned Duration (hrs) | Actual Duration (hrs) | Score | Status
JSON for Automatic Group Detection | 2.0 | 2.0 | 1.0 | Okay
Group-Aware Top K Popular Places Report | 8.0 | 7.9 | 0.99 | Okay
Group-Aware Top K Next Places Report | 11.0 | 10.6 | 1.04 | Okay
Integration | 2.0 | 2.1 | 0.98 | Okay
Make minor changes based on Heuristics Evaluation feedback | 2.0 | 1.6 | 1.22 | Okay
Debugging Pair 1 Functionality | 4.0 | 2.2 | 1.98 | Underrun
Debugging Pair 2 Functionality | 4.0 | 7.3 | 0.55 | Okay

## Slide 9: PPLog Metric
Task Description | Planned Duration (hrs) | Actual Duration (hrs) | Score | Status
JSON for Automatic Group Detection | 2.0 | 2.0 | 1.0 | Okay
Group-Aware Top K Popular Places Report | 8.0 | 7.9 | 0.99 | Okay
Group-Aware Top K Next Places Report | 11.0 | 10.6 | 1.04 | Okay
Integration | 2.0 | 2.1 | 0.98 | Okay
Make minor changes based on Heuristics Evaluation feedback | 2.0 | 1.6 | 1.22 | Okay
Debugging Pair 1 Functionality | 4.0 | 2.2 | 1.98 | Underrun
Debugging Pair 2 Functionality | 4.0 | 7.3 | 0.55 | Okay

## Slide 10: Challenges
Pressure working under deadline (2nd November instead of 4th November)
Working within buffer days
Lack of prior expertise in Design

## Slide 11: Progress Review
All functionalities have been developed
  Minor bug fixes to be done by end of Iteration 5
Implemented all of Supervisor’s feedback
Implemented 7 out of 14 feedback from Heuristics Evaluation
UAT Bugs (7 low, 1 medium)
Core design functions are under development

## Slide 12: Core Focus
Administrative Clean Up
  Final Presentation
  Technical Documentation
  Test Cases
Design Implementation
  Overall layout
  Graphical Components