## Slide 1: Supervisor Meeting 2
G4T7
Aixin Benjamin Ranon Shaun Yiyi

## Slide 2: Agenda
Key Metrics
Deviations
Progress
Roles & Responsibilities
Forging Ahead
Challenges
Mitigation Plans
Summary Recap

## Slide 3: Progress (Past 2 weeks)
Heatmap
Basic Location Report:
  Breakdown by year and gender and school
  Top-k popular places
  Top-k companions
  Top-k next places
Reverting of codes for task 68
PM Review
Technical Documentation
UI – Navigation Bar on Basic Location Report
Debugging of bugs left over from iteration 1 and iteration 2

## Slide 4: Deviation from the planned schedule
PM Review Preparation
Coding task

## Slide 5: Roles and Responsibilities
Task | Pair Programmers | Project Manager
Basic Location Report: Top-k next places Basic Breakdown by year and gender and school | Benjamin, Ranon | YiYi
Heatmap Basic Location Report: Top-k companions Top-k Popular Places | Shaun, Aixin | 

## Slide 6: Schedule Metrics
 | Iterations | (In Days) |  | (In Hours) |  | Metric Score (Days) %
 |  | Planned | Actual | Planned | Actual | 
TOTAL | Iteration 1 | 29 | 28 | 76.5 | 75.5 | 1.04
 | Iteration 2 | 16 | 16 | 70.3 | 75.8 | 1.00

## Slide 7: PPLog Metric
Task Description | Planned Duration (min) | Actual Duration (min) | Score | Status
Heatmap full functionality | 240 | 243 | 1.01 | Okay
Basic Location Report: Basic Breakdown by year and gender and school | 480 | 515 | 1.07 | Okay
Basic Location Report: Top-k popular places | 240 | 244 | 1.02 | Okay
Basic Location Report: Top-k companions | 525 | 545 | 1.04 | Okay
Basic Location Report: Top-k next places | 480 | 682 | 1.42 | Overrun
Integrate with earlier functionalities | 135 | 146 | 1.08 | Okay
Debugging pair 1 functionality | 180 | 161 | 0.89 | Okay
Debugging pair 2 functionality | 330 | 340 | 1.03 | Okay

## Slide 8: PPLog Metric
Task Description | Planned Duration (min) | Actual Duration (min) | Score | Status
Heatmap full functionality | 240 | 243 | 1.01 | Okay
Basic Location Report: Basic Breakdown by year and gender and school | 480 | 515 | 1.07 | Okay
Basic Location Report: Top-k popular places | 240 | 244 | 1.02 | Okay
Basic Location Report: Top-k companions | 525 | 545 | 1.04 | Okay
Basic Location Report: Top-k next places | 480 | 682 | 1.42 | Overrun
Integrate with earlier functionalities | 135 | 146 | 1.08 | Okay
Debugging pair 1 functionality | 180 | 161 | 0.89 | Okay
Debugging pair 2 functionality | 330 | 340 | 1.03 | Okay

## Slide 9: Bug Metrics
BUG SCORE = 33
(8 low, 5 medium)
Bugs were resolved immediately

## Slide 10: Challenges
OpenShift Limitations
  Bootstrap Functionality Affected
    Communications Links Failure
    Proxy Error
Corner Cases not identified during Design phase
  Delay in schedule and task completion
    Top-K Next Places
Changing Wiki requirements
  Delay in schedule and task completion
    Bootstrap and duplicate rows

## Slide 11: Mitigation Plans
OpenShift Limitations
  Clarify requirements with supervisor during Supervisor Meeting
  PM to research on possible solutions
Corner Cases not identified during Design phase
  Reschedule the task and inform the team to account for additional difficulty when corner case is found
  Derive additional robust test cases during Design
    Continuation of SQL Backend Test cases
Changing Wiki requirements
  PM to assign additional tasks to available coders if time and schedule permits
    E.g. Additional validation for Bootstrap (Semantic Place)

## Slide 12: Summary Recap
Iteration 1 & 2
✔
✔
✔
✔

## Slide 13: Forging Ahead
Iteration 3
  Timely end of Iteration 3
    Maintain timely administrative documentation
    Delve into the accuracy of our functionalities
      JSON, Basic Location Reports
Milestone
  Supervisor Meeting for feedback
  Heuristic Evaluation

## Slide 14: Clarifications
OpenShift
  Are we allowed to make adjustments on OpenShift’s PHPMyAdmin?
  What is a reasonable expected time for the bootstrapping of the latest file (data v4)?
Are we supposed to document our SQL queries for our functionalities?
What is an appropriate protocol to document our SQL Backend Test Cases?